E-CLICK / Animal Feed Manufacturers Association (AFMA)

Statement of Work

Entered into by and between

E-CLICK (PTY) LTD

Registration number: 2020/223239/07

(hereinafter referred to as "Contractor")

and

Animal Feed Manufacturers Association (AFMA)

(hereinafter referred to as "the Client")

| Date of submission: | Version: |
| --- | --- |
| 2026 – 04 – 21 | E-Click // AFMA: V.2 |

TABLE OF CONTENTS

1.	Executive Summary	1

2.	Background and Current Environment	2

3.	Objectives of the Engagement	2

3.1 Phase 1 Objective: Website and AFMA STATS Takeover and Stabilisation	2

3.2 Post-Phase 1 Objective: Business-as-Usual Support and Continuous Development	3

3.3 Strategic Objective: Future-State Recommendations and Phase 2 Alignment	3

4.	SCOPE OF WORK	3

4.1 Phase 1 In-Scope Activities	3

4.2 Phase 1 Deliverables	4

4.3 Out of Scope	5

4.4 Future-State Recommendation Principle	6

4.5 Pre-Existing System Condition and Liability Limitation	6

5.	Milestone Plan and Timeline	6

5.1 Phase 1 Milestone Breakdown	6

5.2 Implementation Timeline	7

5.3 Phase 1 Completion Criteria (Definition of Done)	7

5.4 Timeline Dependencies and Constraints	8

5.5 Transition to Ongoing Support	8

6.	Roles and Responsibilities	8

6.1 E-Click Responsibilities	8

6.2 AFMA Responsibilities	9

6.3 Current Service Provider Responsibilities During Handover	9

7.	Takeover, Stabilisation and Support Approach	9

7.1 Takeover Methodology	9

7.2 Stabilisation Activities	10

7.3 Incident, Change and Support Handling	10

7.4 Transition into Service Level Agreement	11

8.	Service Level Agreement Principle	11

8.1 Commencement of Ongoing Support	11

8.2 Continuous Development Approach	11

8.3 Functional Maintenance and Platform Continuity	11

8.4 Commercial Link to Ongoing Support Services	12

9.	Assumptions, Dependencies and Constraints	12

9.1 Access and Information Dependencies	12

9.2 Handover Dependencies	12

9.3 Technical and Operational Assumptions	12

9.4 Timeline Constraints	13

10.	Commercials and Payment Structure	13

10.1 Phase 1 Commercial Basis	13

10.2 Payment Terms	13

10.3 Out-of-Scope Work and Change Requests	13

10.4 Post-Phase 1 Service Support Commercial Approach	14

11.	Acceptance and Sign-Off	14

11.1 Phase 1 Acceptance Criteria	14

11.2 Handover Completion Confirmation	14

11.3 Transition to Service Level Agreement	14

12.	Confidentiality and NDA Reference	14

13.	Dispute Resolution	15

14.	Signature Control	16

15.	Appendix A: Detailed Milestone Breakdown, Cost & Timeline Allocation	17

16.	Appendix B: SLA Monthly Fee and Service Allocation	19

16.1. Monthly SLA Fee	19

16.2. Purpose of the Monthly SLA	19

16.3. Included Within the Monthly SLA Fee	19

16.4. Hosting and Environment Continuity	19

16.4. Support and Maintenance	20

16.5. Backlog and Issue Management	20

16.6. Continuous Development Allocation	20

16.7. Service Allocation Principle	20

16.8. Exclusions From the Monthly SLA Fee	20

16.9. Relationship to Phase 1 Findings	21

16.10. Commercial and Operational Intent	21

17.	Appendix C: Client Onboarding and Financial Setup Information	22

# Executive Summary

This Statement of Work (“SOW”) sets out the basis on which E-Click (Pty) Ltd will undertake Phase 1, being the structured takeover and stabilisation of the AFMA website environment and AFMA STATS system. The purpose of Phase 1 is to enable an orderly handover from the current service provider to E-Click, establish operational control, validate the current environments, confirm hosting and system readiness, and ensure support readiness. Phase 1 is limited to takeover, onboarding, hosting transition where applicable, validation, testing, and stabilisation of the current website platform and AFMA STATS system. It does not include redevelopment, enhancement, or rebuild of either system.

Phase 1 is intended to be completed within a two-week implementation window, subject to the cooperation of AFMA and the current service provider. During this period, E-Click will obtain and validate access, review the existing technical environments, confirm hosting arrangements, test the current systems in their existing condition, identify immediate risks or dependencies, and close out the handover in a controlled and transparent manner.

For clarity, E-Click’s inclusion of the AFMA STATS system in Phase 1 is limited to hosting, transition, validation, and testing to confirm that the existing system is operational in its current condition. Phase 1 does not include investigation, rectification, redevelopment, or liability for pre-existing defects, historical issues, undocumented functionality, or system changes not expressly included in this SOW. Any such items shall be separately scoped and commercially approved. Following successful completion of Phase 1, the parties intend to transition into an ongoing Service Level Agreement (“SLA”) at a total monthly cost of R9,500.00, which shall cover the hosting of the two systems under one licence/subdomain structure together with the agreed support and continuous development framework.

As part of the takeover process, E-Click may also make strategic recommendations regarding future optimisation, phased redevelopment, or potential rebuild of the website environment and related systems where this is justified by maintainability, efficiency, user experience, scalability, or alignment with AFMA’s future digital initiatives. Any such rebuild or redevelopment will be treated as a separate future phase and will be scoped and approved independently.

This SOW therefore provides the practical framework for the Phase 1 way forward, including the scope, milestones, responsibilities, and transition into ongoing support.

# Background and Current Environment

AFMA currently operates a website environment built on WordPress hosted via cPanel, supported by a number of licensed plugins, integrations, backup tools, and SSL services. AFMA also operates the AFMA STATS system, which forms part of the current digital environment to be included in Phase 1.

The current website stack includes, among others, Elementor Pro, Royal Elementor Addons Pro, Backuply Pro, GP Nested Forms, Gravity Forms, Gravity PDF, Mailchimp, Power BI, Updraft Plus, and a Thawte SSL Certificate. The AFMA STATS system includes the existing Feed Sales and Salmonella datasets and is to be onboarded as part of Phase 1 for hosting transition, technical validation, and functional testing in its current state.

At the date of this SOW, the website and related environments remain under the support or involvement of the current service provider. Accordingly, this engagement is structured to allow for a controlled transition of responsibility, with the support and liaison of the existing provider during the initial takeover period.

Phase 1 is therefore intended to provide E-Click with the opportunity to obtain the required access, understand the current technical and operational environments, validate the existing website and AFMA STATS setup and related dependencies, and establish a stable basis from which ongoing support and future development can be responsibly managed.

# Objectives of the Engagement

The objective of this engagement is to enable E-Click to formally assume responsibility for the AFMA website environment in a structured, transparent, and controlled manner.

## 3.1 Phase 1 Objective: Website and AFMA STATS Takeover and Stabilisation

The objective of Phase 1 is to complete the takeover and stabilisation of the current AFMA website environment and AFMA STATS system, including the validation of access, review of the technical environments, confirmation of hosting and key dependencies, identification of immediate risks, testing of the systems in their current condition, and close-out of the handover process with the support of AFMA and the current service provider.

## 3.2 Post-Phase 1 Objective: Business-as-Usual Support and Continuous Development

Upon successful completion of Phase 1, the objective is to transition the website environment and AFMA STATS system into an ongoing support and continuous development arrangement under the Service Level Agreement, to ensure that the systems, hosting, integrations, datasets, and required functionality remain operational, supported, and aligned with AFMA’s needs.

## 3.3 Strategic Objective: Future-State Recommendations and Phase 2 Alignment

A further objective of this engagement is to enable E-Click to assess the current website environment and, where appropriate, make recommendations for future optimisation, phased redevelopment, or rebuild in support of a more efficient, scalable, user-friendly, and future-fit digital environment aligned to AFMA’s broader Phase 2 initiatives.

# SCOPE OF WORK

## 4.1 Phase 1 In-Scope Activities

Phase 1 is strictly limited to the structured takeover, onboarding, hosting transition, validation, testing, and stabilisation of the existing AFMA website environment and AFMA STATS system. No redevelopment or enhancement work is included unless explicitly approved as a change request.

The following activities are included:

ACCESS AND ENVIRONMENT TAKEOVER
Obtain and validate access to all relevant systems, including:

Hosting environment (cPanel or equivalent)

Domain and DNS configuration

WordPress administrative access

AFMA STATS system access and hosting-related access

Third-party services and related dependencies where applicable

Establish secure credential management and access control.

INFRASTRUCTURE, HOSTING AND PLATFORM VALIDATION

Verify hosting configuration, domain routing, and SSL status

Confirm website availability and basic functionality

Confirm AFMA STATS hosting setup and system accessibility

Validate backup mechanisms and recovery capability where applicable

SYSTEM AND DEPENDENCY REVIEW

Audit installed plugins, themes, integrations, and third-party dependencies relating to the website

Review the AFMA STATS hosting and application environment at a practical level sufficient for takeover

Identify versioning, licensing, dependency, and operational risks

FUNCTIONAL VALIDATION AND TESTING

Validate the current website functionality and key workflows

Test the AFMA STATS system in its current condition to confirm whether it is accessible and functionally operational within the transferred environment

Confirm the availability of the Feed Sales and Salmonella datasets in their current operational form

STABILISATION

Ensure the website and AFMA STATS system are operational, accessible, and supportable

Address critical issues only where required to maintain availability, hosting continuity, or prevent system failure

No non-critical fixes, enhancements, optimisations, or redevelopment will be performed during this phase

RISK IDENTIFICATION AND REPORTING

Identify technical risks, vulnerabilities, dependencies, and operational concerns

Highlight areas of technical debt, maintainability concerns, and pre-existing system limitations

Provide a structured findings and recommendations summary

HANDOVER COMPLETION

Establish E-Click as the primary support owner of the website environment and AFMA STATS hosting environment

Confirm readiness for transition into ongoing support services under the SLA

## 4.2 Phase 1 Deliverables

At the conclusion of Phase 1, E-Click will provide:

Access Register

Documented and verified list of all relevant systems, credentials, and access points

Environment Validation Report

Summary of hosting, infrastructure, and platform status for the website and AFMA STATS system

Functional Validation Summary

Practical confirmation of website and AFMA STATS accessibility and operational status in their current transferred condition

Technical Risk & Findings Report

Identified risks, dependencies, limitations, and recommended next steps

Backup & Recovery Confirmation

Verified backup process and recovery capability where applicable

Handover Completion Confirmation

Formal confirmation of successful takeover and support readiness

## 4.3 Out of Scope

The following items are explicitly excluded from Phase 1 unless approved via formal change request:

- Website redesign, redevelopment, or rebuild

- AFMA STATS redevelopment, modification, enhancement, or functional expansion

- UI/UX improvements or content updates

- Performance optimisation beyond critical stabilisation requirements

- SEO, analytics, or marketing enhancements

- Plugin replacement, upgrades, or reconfiguration unless critical for availability

- Bug fixing, data correction, code remediation, or defect resolution relating to pre-existing issues in the AFMA STATS system or website environment

- Any investigation, rectification, redevelopment, or liability relating to historical defects, undocumented functionality, legacy issues, or system behaviour that existed prior to E-Click’s takeover

- New feature development or functional enhancements

- Data restructuring or migration unless required purely for access or hosting continuity

Any work identified during Phase 1 that falls outside this scope will be:

- logged and documented;

- prioritised for post-Phase 1 execution under the SLA or a separate project phase; and

- subject to separate scoping, approval, and commercial agreement.

## 4.4 Future-State Recommendation Principle

During Phase 1, E-Click may identify opportunities for:

Platform optimisation

Architectural improvements

Phased redevelopment or full rebuild

All such recommendations will be:

Clearly documented

Commercially scoped separately

Subject to independent approval by AFMA

No future-state work will be undertaken as part of Phase 1.

## 4.5 Pre-Existing System Condition and Liability Limitation

E-Click’s inclusion of the AFMA STATS system and website environment in Phase 1 is based on the assumption that the systems are provided in an existing working condition suitable for takeover, hosting transition, validation, and support onboarding.

E-Click shall not, by virtue of undertaking Phase 1, assume responsibility or liability for:

pre-existing defects, bugs, failures, or degraded performance;

historical data issues or dataset inaccuracies;

undocumented functionality or legacy system behaviour;

prior development decisions, code quality, or technical debt; or

any remedial development, correction, or enhancement required to bring the systems to a different functional state.

Where such issues are identified, they shall be documented and may be separately scoped and quoted for under a change request, separate project phase, or ongoing SLA process.

# Milestone Plan and Timeline

## 5.1 Phase 1 Milestone Breakdown

Phase 1 will be delivered across the following structured milestones:

Milestone 1: Access Acquisition and Verification

Obtain all required system and platform access for the website and AFMA STATS

Validate credentials and permissions

Identify access gaps or dependencies

Milestone 2: Environment and Hosting Assessment

Review hosting, domain, infrastructure, and platform configuration

Validate website availability, SSL, and related environment controls

Confirm AFMA STATS hosting configuration and accessibility

Milestone 3: System Review and Functional Validation

Audit website plugins, themes, integrations, and dependencies

Review AFMA STATS application environment and datasets at takeover level

Confirm whether the transferred systems are operational in their current condition

Milestone 4: Stabilisation and Support Readiness

Address critical availability issues where required

Ensure both environments are stable and supportable

Establish support readiness and logging approach

Milestone 5: Handover Close-Out and Reporting

Deliver Phase 1 documentation and reports

Present findings, limitations, and recommendations

Confirm formal transition of support responsibility to E-Click

## 5.2 Implementation Timeline

Phase 1 is scheduled to be completed within two (2) weeks from the official project commencement date.

The timeline is structured as follows:

- Week 1:

  - Access acquisition, environment validation, and initial assessment

- Week 2:

  - System review, stabilisation (if required), reporting, and close-out

This timeline is dependent on:

Timely provision of access by AFMA and/or the current service provider

Availability of required system information and documentation

## 5.3 Phase 1 Completion Criteria (Definition of Done)

Phase 1 will be considered complete when the following criteria have been met:

all required system access has been obtained and verified;

the website environment and AFMA STATS hosting environment have been onboarded and validated at a practical level;

the website and AFMA STATS system have been tested in their current condition and confirmed as accessible and supportable, subject to any documented limitations;

backup and recovery processes have been confirmed where applicable;

all identified risks, dependencies, and pre-existing issues have been documented;

no critical blockers to ongoing support remain unresolved; and

all Phase 1 deliverables have been submitted to AFMA and formal handover to E-Click support has been confirmed.

## 5.4 Timeline Dependencies and Constraints

The successful and timely completion of Phase 1 is subject to the following:

Cooperation from the current service provider during handover

Timely access to all required systems and credentials

No unforeseen critical failures within the existing platform

Any delays arising from third-party dependencies or restricted access may result in timeline adjustments.

## 5.5 Transition to Ongoing Support

Upon successful completion of Phase 1:

- the website environment and AFMA STATS system will transition into an ongoing Service Level Agreement (SLA);

- all non-critical findings, historical issues, enhancements, fixes, and improvements will be logged, prioritised, and scheduled under the SLA or future project phases; and

- no additional development, remediation, or enhancement work will be performed without formal approval.

# Roles and Responsibilities

## 6.1 E-Click Responsibilities

E-Click shall be responsible for:

managing and executing the Phase 1 takeover and stabilisation activities in accordance with this SOW;

engaging with AFMA and the current service provider for purposes of technical handover and transition alignment;

reviewing the current website environment, related dependencies, and support requirements;

identifying material risks, access gaps, and stabilisation items relevant to operational takeover;

providing visibility on progress, findings, and close-out readiness during Phase 1; and

preparing for transition into ongoing support following successful Phase 1 completion.

onboarding, hosting transition, and practical validation of the AFMA STATS system in its current condition without assuming liability for pre-existing defects or undocumented issues;

## 6.2 AFMA Responsibilities

AFMA shall be responsible for:

appointing the appropriate representative(s) to coordinate the engagement with E-Click;

ensuring that the required access, information, approvals, and operational input are made available timeously;

facilitating communication and alignment with the current service provider where required;

reviewing and confirming Phase 1 progress, dependencies, and close-out matters; and

confirming acceptance of the Phase 1 deliverables and readiness to transition into ongoing support.

## 6.3 Current Service Provider Responsibilities During Handover

For purposes of an effective and orderly transition, the current service provider shall, where applicable and as coordinated by AFMA, support the Phase 1 handover by:

making the relevant system, hosting, licensing, integration, and access information available;

supporting the transfer or validation of credentials, permissions, technical details, and environment knowledge;

assisting in the clarification of operational dependencies, known issues, and current support arrangements; and

engaging in reasonable liaison during the agreed handover period to support continuity and reduce transition risk.

# Takeover, Stabilisation and Support Approach

## 7.1 Takeover Methodology

E-Click will execute a structured and controlled takeover of the AFMA website environment to ensure continuity of service and minimise operational risk.

The takeover approach includes:

Coordinated engagement with AFMA and the current service provider

Secure acquisition and validation of all required system access

Documentation of the existing environment, configurations, and dependencies

Establishment of E-Click as the primary technical owner for ongoing support

All activities will be conducted in a transparent manner, with progress communicated regularly to AFMA.

## 7.2 Stabilisation Activities

Stabilisation is focused on ensuring that the existing website environment and AFMA STATS system are operational, accessible, hosted correctly, and supportable following the takeover.

Stabilisation activities are limited to:

verification of website availability and core functionality;

validation of hosting, domain, and SSL configuration;

confirmation of AFMA STATS accessibility and hosting continuity;

confirmation of backup processes and recovery capability where applicable; and

resolution of critical issues only, where such issues:

  - prevent the website or AFMA STATS system from functioning; or

  - present an immediate risk to system availability, hosting continuity, or integrity.

For clarity:

stabilisation does not include general bug fixing, system corrections, enhancements, optimisation, or redevelopment;

any non-critical or historical issues identified will be documented and deferred; and

all identified issues and recommendations will be formally recorded and addressed only under post-Phase 1 support arrangements or separate approved scope.

## 7.3 Incident, Change and Support Handling

During Phase 1, all work will be managed in a controlled and prioritised manner:

Incident Handling

Only critical incidents impacting availability or system failure will be addressed during Phase 1

Non-critical incidents will be logged for resolution under the SLA

Change Requests

Any requests for fixes, enhancements, or modifications outside of stabilisation scope will be treated as out-of-scope

Such requests will require:

  - Formal scoping

  - Commercial approval

  - Scheduling under a separate change request or SLA

No Silent Fixes Principle

E-Click will not implement unapproved fixes or enhancements during Phase 1

All additional work will be documented and formally agreed before execution

This approach ensures transparency, cost control, and proper prioritisation of work.

## 7.4 Transition into Service Level Agreement

Upon successful completion of Phase 1, the engagement will transition into an ongoing Service Level Agreement (SLA) for hosting, support, and continuous development of the AFMA website environment and AFMA STATS system.

The SLA will provide a structured framework for:

hosting of the two systems under one licence / subdomain structure;

incident management and resolution;

ongoing maintenance and platform support;

prioritisation and delivery of approved enhancements; and

continuous improvement of the environments.

All items identified during Phase 1 that fall outside stabilisation will be:

logged in a managed backlog;

prioritised in collaboration with AFMA; and

delivered in accordance with agreed SLA terms.

No ongoing support, remediation, or development work will be performed outside of a formal SLA or approved change request.

# Service Level Agreement Principle

## 8.1 Commencement of Ongoing Support

Upon successful completion and sign-off of Phase 1, the parties intend to commence an ongoing Service Level Agreement for the AFMA website environment and AFMA STATS system.

## 8.2 Continuous Development Approach

The purpose of the ongoing support arrangement will be to ensure that the website environment remains maintained, supported, operational, and capable of continuous improvement in line with AFMA’s requirements. This may include support, maintenance, functional enhancements, optimisation, and approved development activities.

## 8.3 Functional Maintenance and Platform Continuity

The ongoing arrangement is intended to support the continued functionality, stability, and performance of the website environment and associated components, including the management of issues, support requests, technical updates, and agreed improvement items.

## 8.4 Commercial Link to Ongoing Support Services

The post-Phase 1 Service Level Agreement shall apply at a total monthly cost of R9,500.00 for the hosting of the two systems under one licence / subdomain structure together with the agreed support and continuous development framework.

Any work falling materially outside the agreed SLA scope shall be subject to separate scoping, approval, and commercial agreement.

# Assumptions, Dependencies and Constraints

## 9.1 Access and Information Dependencies

Phase 1 is dependent on AFMA and, where applicable, the current service provider making the required system access, credentials, technical information, licence details, and related environment information available to E-Click within the agreed implementation period.

## 9.2 Handover Dependencies

The successful completion of Phase 1 is dependent on reasonable cooperation and liaison between AFMA, E-Click, and the current service provider to support the orderly transfer of operational knowledge, environment visibility, and access control.

## 9.3 Technical and Operational Assumptions

This SOW is based on the understanding that the current AFMA website environment and AFMA STATS system are provided in an existing functional condition capable of being reviewed, hosted, tested, and transitioned without immediate redevelopment or major corrective work. E-Click’s Phase 1 scope does not include assumption of liability for pre-existing issues, historic defects, undocumented behaviour, legacy code concerns, or remediation work required to correct system conditions that pre-date takeover.

## 9.4 Timeline Constraints

The intended two-week Phase 1 timeline is subject to the timely receipt of access, information, approvals, and support required for takeover and stabilisation. Any delays in these inputs may affect implementation timing and close-out.

# Commercials and Payment Structure

## 10.1 Phase 1 Commercial Basis

The commercial basis for Phase 1 is aligned to the agreed milestone breakdown, timeline allocation, and effort-based costing as reflected in Appendix A: Detailed Milestone Breakdown, Cost & Timeline Allocation.

Phase 1 is priced at a total value of R18,000.00, based on the agreed milestone allocation and tariff structure.

## 10.2 Payment Terms

The payment structure for Phase 1 shall be as follows:

- a 75% acceptance deposit payable upon approval and acceptance of this SOW and prior to commencement of Phase 1; and

- the remaining 25% final payment payable upon completion of Phase 1 and submission of the final close-out and handover confirmation.

For clarity, the Phase 1 payment breakdown is:

- Acceptance Deposit (75%): R13,500.00

- Final Payment (25%): R4,500.00

E-Click reserves the right not to commence Phase 1 activities until the acceptance deposit has been received, unless otherwise agreed in writing.

## 10.3 Out-of-Scope Work and Change Requests

Any work falling outside the agreed Phase 1 scope, including material enhancements, redevelopment, rebuild activities, or additional services not reflected in Appendix A, shall be treated as out of scope and may only proceed subject to written approval and the applicable commercial agreement.

## 10.4 Post-Phase 1 Service Support Commercial Approach

The commercial basis applicable to the ongoing Service Level Agreement shall be R9,500.00 per month, covering the hosting of the AFMA website environment and AFMA STATS system under one licence / subdomain structure together with the agreed support and continuous development framework. Any material enhancements, redevelopment, or work outside the agreed SLA scope shall be separately scoped and commercially approved.

The detailed monthly fee structure and service allocation applicable to the ongoing Service Level Agreement is set out in Appendix B.

# Acceptance and Sign-Off

## 11.1 Phase 1 Acceptance Criteria

Phase 1 shall be regarded as complete once the agreed takeover and stabilisation activities reflected in this SOW and Appendix A have been completed to a practical standard, including the close-out of the handover process, validation of access and operational readiness, and submission of the Phase 1 findings and handover summary.

## 11.2 Handover Completion Confirmation

At the conclusion of Phase 1, E-Click will provide AFMA with a close-out confirmation recording the status of the takeover, stabilisation activities completed, any immediate risks or outstanding dependencies identified, and readiness to proceed into ongoing support.

## 11.3 Transition to Service Level Agreement

Following AFMA’s confirmation of successful Phase 1 completion, the parties intend to transition into the ongoing Service Level Agreement for the AFMA website environment and AFMA STATS system, under which hosting, continued support, maintenance, and approved continuous development will be governed.

# Confidentiality and NDA Reference

The parties record that a signed Non-Disclosure Agreement (“NDA”) is already in place between E-Click and AFMA in respect of the evaluation, support, and potential service provision relating to AFMA’s digital platforms, including the AFMA website, AFMA STATS system, AFMA Member Management System, and related systems, datasets, documentation, and architecture.

This SOW shall accordingly be read together with that NDA, and all confidential, technical, operational, commercial, and system-related information shared in the course of this engagement shall remain subject to the applicable confidentiality obligations between the parties.

# Dispute Resolution

In the event of any dispute, disagreement, or claim arising out of or in connection with this SOW, the parties shall first seek to resolve the matter in good faith through direct engagement between their authorised representatives. Where the dispute is not resolved within a reasonable period, the parties may escalate the matter to senior representatives of the respective organisations for further resolution. If the dispute remains unresolved, either party shall remain entitled to pursue any rights or remedies available to it in law. This clause shall not prevent either party from seeking urgent or interim relief where such relief is necessary to protect its rights, confidential information, systems, or business interests.

# Signature Control

Client: AFMA

Who warrants that he/she is authorised to do so

| Name & Surname | : |  |
| --- | --- | --- |
| Post Designation | : |  |
| Signature | : |  |
| Date | : |  |
| Location | : |  |

Service Provider: E-Click

Who warrants that he/she is authorised to do so

| Name & Surname | : | Armand Visagie |
| --- | --- | --- |
| Post Designation | : | Manager |
| Signature | : |  |
| Date | : | 2026 – 04 – 21 |
| Location | : | 318 The Hillside Building, Lynnwood, Pretoria, 0081 |

# Appendix A: Detailed Milestone Breakdown, Cost & Timeline Allocation

| Projects | Milestone Code | Milestone Description | Week Allocation | Total Hour Allocation | Tariff | Sub-Total |
| --- | --- | --- | --- | --- | --- | --- |
| AFMA Website Takeover – Phase 1 | P1-W1 | Kick-off and takeover alignment with AFMA and current service provider | Week 1 | 0.5 | R750.00 | R375.00 |
| AFMA Website Takeover – Phase 1 | P1-W2 | Confirm Phase 1 scope, roles, governance, communication cadence and dependencies | Week 1 | 0.5 | R750.00 | R375.00 |
| AFMA Website Takeover – Phase 1 | P1-W3 | Obtain and validate all required access to cPanel, WordPress, domain/DNS, SSL, hosting, backups and third-party services | Week 1 | 2 | R750.00 | R1,500.00 |
| AFMA Website Takeover – Phase 1 | P1-W4 | Review website technical architecture including WordPress core, theme structure, plugins, builders and custom components | Week 1 | 2 | R750.00 | R1,500.00 |
| AFMA Website Takeover – Phase 1 | P1-W5 | Review active licences, plugin compatibility, renewals and ownership responsibilities | Week 1 | 1 | R750.00 | R750.00 |
| AFMA Website Takeover – Phase 1 | P1-W6 | Assess integrations including Mailchimp, Power BI, UpdraftPlus and form/PDF workflows | Week 1 | 2 | R750.00 | R1,500.00 |
| AFMA Website Takeover – Phase 1 | P1-W7 | Review backup, restore readiness, SSL, security posture and immediate operational risks | Week 1 | 1 | R750.00 | R750.00 |
| AFMA Website Takeover – Phase 1 | P1-W8 | Conduct outgoing provider handover workshop and compile current-state findings and risk register | Week 1 | 2 | R750.00 | R1,500.00 |
| AFMA Website Takeover – Phase 1 | P1-W9 | Close outstanding handover gaps and confirm operational readiness for takeover | Week 2 | 1 | R750.00 | R750.00 |
| AFMA Website Takeover – Phase 1 | P1-W10 | Validate website functionality, forms, notifications, PDFs and integration continuity | Week 2 | 3 | R750.00 | R2,250.00 |
| AFMA Website Takeover – Phase 1 | P1-W11 | Confirm support workflow, incident logging, response process and change approval approach | Week 2 | 1 | R750.00 | R750.00 |
| AFMA Website Takeover – Phase 1 | P1-W12 | Finalise takeover report, handover notes and Phase 1 close-out workshop | Week 2 | 1 | R750.00 | R750.00 |
| AFMA Website Takeover – Phase 1 | P1-W13 | Compile Phase 2 backlog and development recommendations for AFMA STATS and AFMA Member Management System | Week 2 | 1 | R750.00 | R750.00 |
| AFMA STATS Takeover, Hosting & Validation – Phase 1 | P2-W1 | Obtain and validate all required access to AFMA STATS environment, hosting and related credentials | Week 1 | 1 | R750.00 | R750.00 |
| AFMA STATS Takeover, Hosting & Validation – Phase 1 | P2-W2 | Review current AFMA STATS hosting and application environment including Feed Sales and Salmonella datasets | Week 1 | 1 | R750.00 | R750.00 |
| AFMA STATS Takeover, Hosting & Validation – Phase 1 | P2-W3 | Validate system accessibility, hosting continuity and current operational condition | Week 2 | 1 | R750.00 | R750.00 |
| AFMA STATS Takeover, Hosting & Validation – Phase 1 | P2-W4 | Perform practical functional testing and record risks, limitations and dependencies | Week 2 | 2 | R750.00 | R1,500.00 |
| AFMA STATS Takeover, Hosting & Validation – Phase 1 | P2-W5 | Confirm support readiness and include AFMA STATS findings in Phase 1 close-out | Week 2 | 1 | R750.00 | R750.00 |
|  |  |  | Total | 24 |  | R18,000.00 |

Table 1: Appendix A

# Appendix B: SLA Monthly Fee and Service Allocation

Following successful completion and sign-off of Phase 1, the parties intend to transition into an ongoing Service Level Agreement (“SLA”) for the AFMA website environment and AFMA STATS system. The SLA monthly fee is intended to provide AFMA with a structured framework for the ongoing hosting, support, maintenance, and continuous development of the two systems under E-Click’s operational management.

## 16.1. Monthly SLA Fee

The monthly SLA fee shall be:

R9,500.00 per month

This monthly fee shall apply to the combined support structure for:

- the AFMA website environment; and

- the AFMA STATS system, including the Feed Sales and Salmonella datasets environment,

hosted and managed under one agreed licence / subdomain / operational support structure.

## 16.2. Purpose of the Monthly SLA

The purpose of the SLA is to ensure that, following Phase 1 takeover and stabilisation, the relevant AFMA systems remain:

- hosted and operational;

- supported within an agreed support framework;

- maintained from a platform continuity perspective;

- monitored for support-related issues and operational risks;

- capable of receiving approved continuous development and improvement over time.

## 16.3. Included Within the Monthly SLA Fee

The monthly SLA fee is intended to include the following ongoing service components:

## 16.4. Hosting and Environment Continuity

- hosting of the AFMA website environment;

- hosting of the AFMA STATS system environment;

- management of the two systems under the agreed licence / subdomain structure;

- practical oversight of environment continuity and operational availability.

## 16.4. Support and Maintenance

- day-to-day support oversight for the hosted systems;

- review and handling of reported incidents or support requests;

- reasonable technical maintenance required to keep the environments supportable;

- coordination of support actions required for continuity and operational stability.

## 16.5. Backlog and Issue Management

- logging and tracking of issues, findings, and support items identified during Phase 1 or thereafter;

- prioritisation of items in consultation with AFMA;

- management of a practical support and improvement backlog.

## 16.6. Continuous Development Allocation

- inclusion of a reasonable ongoing development and improvement component within the monthly support structure;

- delivery of approved minor enhancements, support-related updates, or functional improvements as prioritised under the SLA framework;

- structured planning of larger changes or development items for separate approval where required.

## 16.7. Service Allocation Principle

The SLA monthly fee is intended to support the continued operational management of the AFMA website environment and AFMA STATS system on a practical and commercially controlled basis.

For clarity, the monthly fee is intended to cover:

- hosting and continuity of the two systems;

- reasonable support and maintenance effort;

- structured support administration and coordination;

- prioritised continuous development within the agreed SLA framework.

The SLA does not create an unlimited development obligation and does not include unrestricted fixes, enhancements, or redevelopment work.

## 16.8. Exclusions From the Monthly SLA Fee

Unless otherwise agreed in writing, the following are excluded from the monthly SLA fee:

- major redevelopment or system rebuilds;

- large functional expansions or new module development;

- major data restructuring, migration, or correction exercises;

- remediation of significant legacy defects requiring separate technical investigation or redevelopment effort;

- third-party licensing, subscription, or external service cost increases unless expressly included;

- ad hoc work materially outside the agreed support and development framework.

Any such items shall be separately scoped, quoted, and approved before execution.

## 16.9. Relationship to Phase 1 Findings

Any non-critical issues, technical debt, historical defects, undocumented functionality, or future development requirements identified during Phase 1 shall be:

- logged and recorded by E-Click;

- prioritised with AFMA;

- addressed either:

  - within the reasonable bounds of the SLA framework; or

  - through separate scoping and approval where the required effort falls outside the intended monthly support allocation.

## 16.10. Commercial and Operational Intent

The SLA monthly fee is intended to provide AFMA with a stable and predictable support structure following Phase 1, while ensuring that E-Click can responsibly host, support, maintain, and progressively improve the website and AFMA STATS system without ambiguity as to scope, support responsibility, or commercial basis.

SLA Monthly Fee and Service Allocation Summary:

| Item | Description |
| --- | --- |
| Monthly SLA Fee | R9,500.00 per month |
| Systems Covered | AFMA Website Environment + AFMA STATS System |
| Hosting Basis | Combined hosting / licence / subdomain structure |
| Included Services | Hosting, support, maintenance, backlog management, continuous development |
| Excluded Services | Major redevelopment, rebuilds, large enhancements, major data remediation, out-of-scope work |
| Commercial Rule | Material work outside the SLA scope to be separately scoped and approved |

# Appendix C: Client Onboarding and Financial Setup Information

Client Entity Information

| Item | Information |
| --- | --- |
| Registered Entity Name |  |
| Trading Name (if different) |  |
| Company Registration Number |  |
| VAT Number (if applicable) |  |
| Income Tax Number (if applicable) |  |
| Type of Entity | Sole Proprietor / Partnership / Private Company / Public Company / Association / Other |
| Country of Incorporation |  |
| Country of Tax Residency |  |

Registered and Billing Address Information

| Item | Information |
| --- | --- |
| Registered Physical Address |  |
| Postal Address |  |
| Billing Address (if different) |  |

Primary Client Contact Information

| Item | Information |
| --- | --- |
| Primary Contact Person |  |
| Designation |  |
| Contact Number |  |
| Email Address |  |

Accounts Payable / Finance Contact Information

| Item | Information |
| --- | --- |
| Accounts Contact Person |  |
| Designation |  |
| Contact Number |  |
| Email Address for Invoices |  |
| Secondary Accounts Email (if applicable) |  |

Financial Allocation Information

| Item | Information |
| --- | --- |
| Purchase Order Required for Invoicing? | Yes / No |
| If yes, PO Number or PO Process to be followed |  |
| Preferred Invoice Reference |  |
| Client Account Code / Internal Reference (if applicable) |  |
| Invoice Currency | ZAR / USD / EUR / Other |
| VAT Treatment | Standard VAT |
| Preferred Invoice Issue Method | Email / Portal / Other |
| Preferred Payment Term | 7 Days / 15 Days / 30 Days / Other |
| Estimated Monthly Spend (if applicable) |  |

Client Declaration

The undersigned confirms that the information provided above is true and correct and may be used by E-Click (Pty) Ltd for purposes of client onboarding, financial setup, invoicing administration, account allocation, and service delivery coordination.

| Item | Information |
| --- | --- |
| Name and Surname |  |
| Designation |  |
| Signature |  |
| Date |  |